## A - Roles & Responsibilities
ONLINE COURSE DEVELOPMENT AND INSTRUCTIONAL DESIGN SUPPORT - Roles & Responsibilities
Does the staff you are proposing meet all the required criteria below?
Subject Matter Experts
Instructional Designers
Project Managers
Technological Experts
ADA Specialists
Graphic Designers
Subject Matter Experts must:
• | Have 3-5 years of professional experience in their relevant field, if designing continuing education courses.
• | Be well-versed in a variety of academic disciplines and subject areas, with at least two (2) years of experience designing courses for online delivery.
• | Be familiar with the Quality Matters standard rubric for course design and possess a similar course design certification.
• | Have a performance history of producing engaging, contemporary and ADA accessible quality eLearning content for credit and continuing education courses, according to industry standards.
• | Have a familiarity with how to employ Cengage, MindTap, Pearson MyLab and McGraw-Hill into the online learning course experience.
Instructional Designers must:
• | Possess a performance history of ensuring subject matter experts produce engaging, contemporary and ADA accessible quality eLearning content, according to industry standards.
• | Have experience designing learning objects, using Articulate or a similar technology tool.
• | Create 16, 12 and 8 week online course shells for the courses where faculty internal subject matter experts are not available.
• | Create the 12 week and 8 week course shells during the time faculty internal subject matter experts are creating the 16 week shells.
• | Be highly proficient with utilizing the D2L Brightspace learning management system.
• | Have a familiarity with Blackboard Ally, the integrated learning management universal design accessibility tool.
• | Know how to integrate Cengage, MindTap, Pearson MyLab and McGraw-Hill into the online learning course experience.
Project Managers must:
• | Be skilled with using a project management tool, similar to Smartsheet.
• | Have experience in higher education collaborating with administrators, faculty, and other staff to manage the development of new online courses or the revision of existing online courses.
• | Have experience collaborating with college administrators to help assess the health of each new or existing course during the course design process to ensure deadlines are met and courses are launched on schedule.
• | Provide a real-time dashboard that converts data into visuals of trends and metrics, so that stakeholders can view the progress and health of course development projects with ease and convenience.
Technological Expert must:
• | Collaborate between system users, system support personnel, and vendors to identify and resolve issues.
• | Interpret, analyze, diagnose, document and resolve customer support issues related to enterprise technologies.
• | Facilitate problem solving among administrative groups with varying needs and priorities.
• | Communicate to administrative users, technical staff, and senior level management in a user-friendly language.
• | Identify and obtain appropriate resources for the resolution of complex problems; correct routine problems; contact appropriate resources for additional assistance when appropriate.
• | Work collegially with a diverse set of faculty and staff to empower them in the appropriate, effective use of educational technologies.
ADA Specialist must:
• | Review the newly developed and revised courses during the design process to ensure CCC is meeting the ADA accessibility standards as outlined in Section 508 of the Rehabilitation Act under the Information
• | and Communication Technology (ICT) accessibility standards and Section 255 of the Communications Act.
• | Recommend alternative and accessible learning tools to our in-house faculty so that documents and other items meet accessibility requirement prior to those items being uploaded into the course.
• | Assist with updating documents in courses that Blackboard Ally, an integrated accessibility tool designed to monitor and measure courses for accessibility compliance, identifies as non-compliant documents.
• | Ensure all newly developed or revised courses possess a Blackboard Ally score of 80% or more.
Graphic Designers must:
• | Have familiarity with D2L Brightspace Learning Management System (LMS).
• | Create well designed focal points that guides learners as they study, draws attention to the most important parts of a course and highlights important items to remember.
• | Create designs that help to improve readability for highly technical topics with the use graphic design elements like font, layout, and white space.
• | Ensure that every design component aligns with the subject matter by turning complex ideas into easily digestible graphs, charts, and tables.
• | Combine the two essential traits of creativity and having an eye for detail, to visualize the outcome of an eLearning course design.
• | Be able to create rough sketches and storyboards to help the client visualize the overall eLearning course design.
• | Be able to revise design based on the overall feedback.

## B - Service Related Questions
ONLINE COURSE DEVELOPMENT AND INSTRUCTIONAL DESIGN SUPPORT - Service Related Questions
| 1.1 | Online Instructional Design and Course Development Service (What is included in your proposal costs) | Yes/No | Included in Proposal Cost
Initial analysis of potential cost savings to CCC, such as pre-designed content for continuing education courses?
All associated costs for supplying instructional designers, project managers, technology specialists, the ADA specialist, and other other personnel required to complete the two year course design project?
Subscriptions or licenses that will be attached to the current services, such as Smartsheet, Articulate or Adobe?
Consulting/training fees for learning how to use vendor provided software, or other services?
Software or digital resources in order to support your company with providing course design services?
Providing cost containment strategies so that CCC can remain within the allocated budget throughout the entire project?
Weekly, monthly and annual reports in a dashboard format to show progress, challenges and completion of the project.
A plan for CCC to maintain the simulations, games or learning objects that are created once your services have ended?
A single point of contact for all service related issues
A plan for the technical support your company will provide? Will there be an extra charge for this support if it exists?
| 1.2 | Does your company have a plan to ensure that each designed course is designed as a quality course, as determined by the Quality Matters standard rubric
and by eLearning universal design standards?
Does your company have its own rubric to measure the quality of all course content and any related learning tools (simulations, games or learning objects)?
Discuss how your company uses the Quality Matters rubric to design credit courses. If your company does not use Quality Matters to design credit courses, please discuss what universal course design method you use.
| 1.3 | Can your company create learning objects, simulations, games or other visual learning tools?
Describe what technological tools your company needs to create these learning tools. Explain what CCC will need to do to support your technological needs.
| 1.4 | Has your company provided services to community colleges, where you performed course design?
Please provide examples of the written content and additional learning tools (learning objects, simulations and/ or games) you designed for their courses.
| 1.5 | Has your company provided services to non-for-profit colleges or universities?
Please provide examples of the written content and additional learning tools (learning objects, simulations and/ or games) you designed for their courses.
| 1.6 | Is your service/support structured for multi-year forecasted needs?
What strategy does your firm utilize to manage and forecast an instructional design and course design package over a 2 year period?
| 1.7 | Are you willing to provide performance guarantees to CCC for your services?
If yes, please provide examples.
| 1.8 | Do you have a documented process/procedure for dealing with course design delays?
How involved are you willing to be in terms of issues that may require intervention or solution support between your company and the CCC staff related to course design delays?
| 1.9 | Have you specifically created online programs for hospitality management, addiction studies, cybersecurity, media communications, social work, web design,
and human development and family services ?
Please provide examples of course content in two of these areas.
| 1.1 | Is there a designated team member that would be the liaison for content design or technological questions that may arise?
Describe the action that would be taken, the support provided, and the personnel who would be involved in providing support for the these services.
| 1.11 | Are there conversations that occur (monthly, quarterly, etc.) regarding solutions for future course design modifications ?
What is your process, and what resources do you have available, for program recommendations?
| 1.12 | CCC will provide access to D2L Brightspace learning management system, as well other technology your company may need. Are there tools/websites that CCC
may have access to on your end?
List the in-house tools available to CCC (i.e. web based support). Provide demo website and password for our perusal.
| 1.13 | Will you present a plan for designing credit courses in an 8 week cycle?
If so, how will track the milestones in this course design model? Describe your process for tracking milestones.
| 1.14 | Is your implementation strategy customized to each customer? Our credit online courses are designed in a 15 week design cycle, but we are open to modifying
this cycle to develop more credit courses from January 2022 to June 2024.
What is the process and the time frame if we want to explore alternative design time frames?
| 1.15 | Describe your firm’s expertise in each of the following areas: Tell us how you separate yourselves from other firms in each of these arenas. Please site specific examples.
Course Content-utilizing the Quality Matters Rubric or other standardized universal course design
Course Learning Tools, i.e. simulations, games, learning objects, etc.
Course Accessibility-ensuring designed courses comply with ADA accessibility manadates and standards, as well as appeal to diverse learning styles and students
Course Design-the ability to effectively and efficiently design customized courses in an 8 week or 15 week design cycle.
Cost Effectiveness-providing an inclusive package of services without add-ons throughout the terms of the contract.
Customer Service-providing key individuals to assist with training, technological issues and course design resolutions.
Course Maintenance-once the contract ends CCC can maintain the courses on its own.

## C - Current Milestones & Tasks
ONLINE COURSE DEVELOPMENT AND INSTRUCTIONAL DESIGN SUPPORT - Current Course Design Milestones & Tasks
Example of current Course Development & Revision schedule - Please use this information to plan your scheduling and staffing proposal
Schedule or Project Timeline:
Example of a Fall 2021 Course Timeline
New Course Development and Course Revision-FALL 2021
COURSE DEVELOPMENT and COURSE REVISION TIMELINE
Meeting 1- SEPTEMBER 13-14 (depending on faculty’s schedule)
Kick off Meeting (a recording will be provided for those who cannot attend.)
Meeting 2- SEPTEMBER 20-24 (depending on faculty’s schedule)
Progress meeting
Due October 1st – Textbook Selection (Task 1)
Meeting 3- OCTOBER 4-8 (depending on faculty’s schedule)
Progress meeting
Due October 15th – 16-week, 12-week and 8-week Master Syllabi (Task 2)
Meeting 4-OCTOBER 18-22 (depending on faculty’s schedule)
Progress meeting
Due October 29th – build weeks 2, 3, 4 and 5 in Brightspace (Task 3)
Meeting 5-NOVEMBER 1-5(depending on faculty’s schedule)
Progress meeting
Due November 12th – build weeks 6, 7, 8 and 9 in Brightspace (Task 4)
Meeting 6-NOVEMBER 15-19 (depending on faculty’s schedule)
Progress meeting
Due November 29th – build weeks 10, 11, 12 and 13 in Brightspace (Task 5)
Meeting 7-NOVEMBER 29-DECEMBER 4 (depending on faculty’s schedule)
Progress meeting
Due December 10th – build modules 14, 15 and 16 in Brightspace (Task 6)
Meeting 8- DECEMBER 6-11 (depending on faculty’s schedule)
Progress meeting
Due December 17th – final approval of the course (Task 7)
Meeting 9- DECEMBER 13-17 (depending on faculty’s schedule)
Final/Wrap-up meeting
CHECK POINT FOLLOW-UPS: (PM will check in with faculty to ascertain any challenges with completing the tasks at the appropriate time via email.)
TASK 1: Select one main textbook/resource and two alternatives. If all resources will be OER, please find alternatives just in case something happens.
START: MONDAY, SEPTEMBER 13: END: FRIDAY, OCTOBER 1
NOTE: In some cases, departments may select the textbook and/or resources for a myriad of reasons. SMEs are expected to comply with the departmental mandate, and use the resources suggested/required by the department.
FINALIZE TEXTBOOK SELECTION BY OCTOBER 1 OR BEFORE
· Identify list of textbooks/resources for review or begin reviewing department directed textbook/resources.
· Please ask the publisher if the textbook is a new edition, or an old edition. If it is an old edition, please ask the publisher when the edition will cease being used. You will want to adopt the new edition. If the new edition will be available the semester after your course is being developed or revised, we will need to meet with you to discuss your options.
Order copies of all the books that are currently being used and any others the team may be interested in (if necessary).
Publishers can be identified to do presentations and/or provide access to additional resources and technology (ID works with academic leads and dept. sec. to order the textbooks/resources for the design team).
Order copies of potential textbooks/resources for SMEs (academic leads work with dept. secretary)
Review textbooks/resources (SMEs).
Identify primary and ancillary content and texts (SMEs)
Course materials and textbook selection.
Finalize decision on textbook/resources utilize book review instrument(s).
ID assists by providing feedback on technologies and supplemental textbook/resources.
Decide on the textbook/resources to use.
Ensure course textbook/resources have sufficient materials that are conducive to distance learning environment (online, videos, simulation, web resources, pretests, articles and so on...)
If you plan to use an integrated resource like Connect or MindTap, please make sure there aren’t any technological issues with integration. Please work with your academic lead or department to order enough access codes.
Select three textbook/resource choices from your research. One of the textbooks/resources will be the one you will use in the course, the other two will be alternatives for any other faculty member to use. All textbook/resources support the SLOs and COs of the course.
Submit your textbook/resources choice to your academic lead or department. The bookstore will need this information one full month before it opens its portal to students.
Deliverables: SMEs will provide ID/PM with proposed/desired textbooks/resources information. Textbooks/resources will be ordered for review. The textbook/resources will be ordered during this time to be available in the bookstore for Spring 2022. Using Open Educational Resources (OER) in your courses may allow for a richer academic experience, and a lesser chance of needing to revise the course due to discontinued textbooks or editions.
TASK 2: Develop Master Syllabi
START: MONDAY, SEPTEMBER 27 END: FRIDAY, OCTOBER 15
Develop Master Syllabi for online learning: 16 week, 12 week and 8 week
Identify types of assessments and align to outcomes.
Determine what the best type of assessments (quizzes, discussion boards, etc.) are to meet the SLOs and COs, utilize Bloom's Taxonomy.
Determine point values for each assignment, discussion board and assessment.
IDs will provide feedback on these alignments.
Multiple forms of assessments should be considered (group work, reflection paper, discussion, labs, research paper, etc.)
· ID reviews course syllabus development
SYLLABI ARE DUE NO LATER THAN OCTOBER 15
Deliverables: Develop and submit syllabus to ID. ID reviews and assist instructor in developing the course outline and provides feedback throughout the process.
TASK 3: Start building weeks 2, 3, 4 and 5 in Brightspace.
START MONDAY, OCTOBER 18: END FRIDAY, OCTOBER 29 (Mid-terms for 16 week courses occur on the Academic Calendar starting on Oct. 24.)
Build modules 2, 3, 4 and 5 for ID Review (module 1 is the “Getting Started Week, which is already built.)
Develop and organize course content for online delivery (use QM Rubric-Alignment section as the main source for content creation)
Develop weekly course materials.
There would be a total of 16 content weeks for 16-week course.
First week is introduction and last would be for the final assessment for a total of 16 weeks.
IDs will work closely with SMEs to develop assignments and make sure everything is optimized for online.
Flesh out assignments including directions for how to complete and submit the assignment. Ensure point values align with the 16 week syllabus.
Create activities during these weeks.
Example activities:
Create lesson content. Build weekly interactions.
Develop assessments.
Develop grading scheme and supporting rubric.
Develop lessons and media rich audio/video content in consultation with your instructional designer.
Develop rubrics.
Deliverables: Develop weeks in Brightspace shell for weekly activities.
TASK 4: Start building weeks 6, 7, 8 and 9 in Brightspace.
Respond to feedback from IDMs about missing content, additional content, etc. in weeks 2,3,4 and 5.
START MONDAY, NOVEMBER 1: END FRIDAY, NOVEMBER 12
Develop and organize course content for online delivery (use QM Rubric-Alignment section as the main source for content creation)
Develop weekly course materials.
There would be a total of 16 content weeks for a 16-week course.
Weeks 6, 7, 8 or 9 should be considered as the mid-term module and the last module should be for the final assessment.
Flesh out assignments including directions for how to complete and submit the assignment. Ensure point values align with the 16 week syllabus.
Create activities during these weeks.
Example activities:
Create lesson content. Build weekly interactions.
Develop assessments.
Develop grading scheme and supporting rubric.
Develop lessons and media rich audio/video content in consultation with your instructional designer.
Deliverables: Develop weeks in Brightspace shell for weekly activities.
Thanksgiving Break occurs NOVEMBER 25-26 on the Academic Calendar. FACULTY ARE NOT REQUIRED TO WORK DURING THE HOLIDAY.
TASK 5: Start building weeks 10, 11, 12 and 13 in Brightspace.
Respond to feedback from IDMs about missing content, additional content, etc. in weeks 6, 7, 8 and 9.
START MONDAY, NOVEMBER 15: END MONDAY, NOVEMBER 29
Develop and organize course content for online delivery (use QM Rubric-Alignment section as the main source for content creation)
Develop weekly course materials.
There would be a total of 16 content weeks for a 16-week course.
Weeks 6, 7, 8 or 9 should be considered as the mid-term week and the last week should be for the final assessment.
Flesh out assignments including directions for how to complete and submit the assignment. Ensure point values align with the 16 week syllabus.
Create activities during these weeks.
Example activities:
Create lesson content. Build weekly interactions.
Develop assessments.
Develop grading scheme and supporting rubric.
Develop lessons and media rich audio/video content in consultation with your instructional designer.
Deliverables: Develop weeks in Brightspace shell for weekly activities.
TASK 6: Start building modules 14, 15 and 16 in Brightspace.
Respond to feedback from IDMs about missing content, additional content, etc. in weeks 10, 11, 12 and 13.
START TUESDAY, NOVEMBER 30: END FRIDAY, DECEMBER 10 (Last day of the term is December 11.)
Develop and organize course content for online delivery (use QM Rubric-Alignment section as the main source for content creation)
Develop weekly course materials.
There would be a total of 16 content weeks for a 16-week course.
Flesh out assignments including directions for how to complete and submit the assignment. Ensure point values align with the 16 week syllabus.
Create activities during these weeks.
Example activities:
Create lesson content. Build weekly interactions.
Develop assessments.
Develop grading scheme and supporting rubric.
Develop lessons and media rich audio/video content in consultation with your instructional designer.
Deliverables: Develop weeks in Brightspace shell for weekly activities.
ALL MODULES COMPLETED BY SME NO LATER THAN DECEMBER 10
Checklist of completed course
 Develop and submit course syllabi-16,12, 8 week
 16 week syllabus should match the Brightspace shell
 8 week syllabus should reflect a realistic timeframe to complete the work.
 Building the course shell
 Descriptions of modules
 Assignments
§ Assignment instructions
§ Points allocated
 Assessments
§ Assessment instructions
§ Points allocated
 Discussion questions
§ Posting discussion responses instructions
§ Points allocated
 Rubrics
 Descriptive links
 Instructions for watching videos or viewing PowerPoints
 Make sure graded assignments and assessments are linked to the Gradebook
TASK 7: Final Approval of the Course
START: MONDAY, DECEMBER 13 END: FRIDAY, DECEMBER 17
ID sign off.
Deliverables: Develop weeks in Brightspace shell for weekly activities.
Finalize course review and provide detailed feedback based on QM standards. Any suggestions and final updates will be provided to faculty.
COURSE REVIEW / COURSE REFLECTION-SPRING 2022
START: MONDAY, JANUARY 3, 2022 END: FRIDAY, JANUARY 7, 2022
Course review tour. SMEs will host a 30 minute review of the newly developed or revised course for their colleagues who will teach the course in the SP22 semester. If the faculty members are unable to meet before school begins, the SMEs will record a 10 minute review of the course that will be placed in the master shell under the “Read Me” module.
START: MONDAY, APRIL 18, 2022 END: FRIDAY, APRIL 22, 2022
The PM will disseminate a survey 12 weeks after the course has been piloted.
Instructors are encouraged to reflect on how the course content is delivered and the impact the material has on student learning.
Deliverables: Develop weeks in Brightspace shell for weekly activities. Assessment on student participation, retention rate, student grades/score for each activity, complaints from students and any other related issues. Review student and instructors’ feedback. Update course based on feedback.

## D - Cost Proposal
ONLINE COURSE DEVELOPMENT AND INSTRUCTIONAL DESIGN SUPPORT - Cost Proposal
Please provide the hourly cost associated with the design or revision of the courses, based on level of expertise/role of provider
| New Course Design | Existing Course Revisions | Continuing Education Courses
Number of courses | 85 | 50 | 20
Subject Matter Experts
Instructional Designers
Project Managers
Technological Experts
ADA Specialists
Graphic Designers
Please list any other costs associated with this initiative, including (but not limited to): materials, overhead, technology related costs, service fees, support costs (technical and operational), licensing, etc.
Type of cost |  | Cost | Unit (ea, hr, annual, etc.) | Type of cost | Cost | Unit (ea, hr, annual, etc.)
Within your proposal package that will be submitted along with the information provided above, please provide a thorough breakdown of ALL costs, fees and charges associated with your company managing and executing the program as outlined in the RFP package.